## Slide 1: Software Development Process
Name: Vlad Rakocevic
Title: Software Development Eng. Manager
Company Name: Apcon

## Slide 2: Definitions
Software
      Any programs or instructions intended to run on a programmable device, including firmware, operating systems, drivers, applications, utilities, shell scripts, makefiles, CLI, UI, Titan, etc
Third Party Software
      Any software, source or binary, not developed by Apcon Personnel. In addition to source code, this does include tools such as compilers and libraries, utilities, editors, etc. For example, gcc and glib qualify as Third Party Software
Source Code
      All product and test sources, makefiles, scripts, MIB modules, etc. that contribute to the product
Software Project Lead
      The individual(s) responsible for coordinating the development of the software product by following the Software Development Process, as identified in the project’s Software Project Plan. This role is the focal point for a project and is typically a Program, Project, or Engineering Manager, but can be anyone assigned to the role.
Validation
      The process of ensuring that a product meets the customer’s needs.
Verification
      The process of ensuring that a product meets its specification.

## Slide 3: Scope of the document
Scope
  This document applies to all Apcon personnel developing software for its products, including all firmware and UI software, and all test software used for formal testing of Apcon products.
  This document is mandatory for the Plano, TX and Wilsonville, OR design centers.
  The scope of this document is limited to design and development stages required producing software components based on defined and approved requirements

## Slide 4: Training Requirements
This document shall be given to software developers and managers when hired and notice sent to existing software developers and managers when this document is updated

## Slide 5: Software Development Phases
Phases
  Typically, the development effort is divided into 5 distinguish phases: Investigation, Specification and Design, Implementation and designer debug, Verification, and Release to QA. Each of these phases produce a number of documents and outputs, tailored to the size and complexity of the project, as documented in the Software Project Plan (SPP).
  The development phases are rarely serialized. Parallelism and iterative nature of development are implicit to this process and should be honored.
Where projects cross organizational boundaries, entry and exit criteria should be defined and addressed in the SPP

## Slide 6: Investigation Phase
The purpose of this phase is to deliver the documents required for the purpose of evaluating the cost of developing software features and the benefits and return on that investment.
This phase focuses on the investigation aspect of the project and provides a preliminary schedule, a resource profile, and overall cost for the project that can be applied to the ROI analysis. In this phase:
  The Product Line team produces the product requirement documents which are reviewed and approved in this stage
  SW Engineering team responds to the PRD requirements with early feasibility studies and a road map plan that consists of a document outlining which software features will be available in what release. This document is known as RFD (Release Feature Document) and specifies features and requirements available in the follow up software releases. Note that RFD is not a must have documentation; many sw initiative may not require RFD.
  a Release Features Document is reviewed and approved in this phase
  a High Level Schedule that details major delivery milestones is completed and approved
  a Engineering Estimate ( a spreadsheet or other electronic format) is completed and approved. It includes hardware and equipment cost , external spend (if development requires external contractors, sw tools and licenses, payment for customized development from Apcon’s vendors and suppliers, etc…), and the labor cost for developing, verifying, validating and releasing software

## Slide 7: Investigation Phase flow chart and deliverables
High level Product Requirements Document
  Owned by the PLM. Contribution from Marketing, Engineering and Pro-Services teams. Reviews driven by PLMs
Engineering cost estimate
  It is an electronic document capturing the effort, external spend and project spend for the proposed feature(s). It is a high level estimate and is roughly +/- 20% correct. Owned by Engineering team (typically SW and HW Managers).
  High Level schedule – an MSPP document owned by a PM with the inputs from HW, SW, and QA managers. Considers resource availability and competing releases and projects going in parallel.
Senior Management team reviews projected engineering cost and schedule and makes a decision to proceed with development or to cancel or postpone it.

## Slide 8: Specification and Design Phase
The purpose of this phase is to complete the software planning and design.
The specification and design documents define the design and the criteria for verifying the design and the functionality of the development output.
Documents that may be delivered in this phase include:
• a Software Project Plan (SPP) approved to a 1.0 revision level
• software specifications documents
• software design documents
• unit and functional test plans
• Software QA Entrance Criteria Agreement

## Slide 9: Specification, Development and Verification

## Slide 10: Implementation and designer debug phase
The purpose of this phase is to complete the coding of software features and requirements and specified testing.
Every completed software feature is verified initially by the sw implementers via execution of designers’ test tools or test drivers, test scripts, or stepping through the code debugger.
The format of the designer test plan is open and doesn’t not need to conform to a particular form. However, it is required that every sw feature and requirement is verified by the author according to sw design specs and Engineering Requirements, when practical.
Activities that take place in this phase are:
  Creation of detail design specs
  Review of detail design specification or alternatively “pseudo” code
  Implementation of sw features and requirements
  Code reviews
  Designer verification of the feature and requirements
Documents that may be delivered in this phase include detailed design documents, source code, code reviews, defect reports, and design debug execution reports.

## Slide 11: Implementation and designer debug phase
Implementation of a sw feature
  Starts with creation of a Mantis new-feature issue
  Submission of the feature code to code repository database includes the reference to Mantis issue number as well as a reference to code review instance
  Author must create and drive both pseudo code and code complete review by initiating a Code Review instance/session that also includes reference to the Mantis issue number
  Submission activity to the code repository database of designer verified code includes reference to the Mantis issue number. Code Submission pre-checker tool verifies the validity of the Mantis Issue and rejects the submission if not valid
  Upon code submission into repository, Apcon in-house developed tool updates the Mantis issue description field with the links to code review instance ref number and code submission activity identifier.

## Slide 12: Verification Phase
In this phase software development team (including the development test engineers) defines the test strategy, test cases and creates the test plans for unit and functional testing.
The focus of the unit and functional testing is to verify that the software features implementations conform to software requirements at the higher level than the designer level implementation.
Typically at the unit level Apcon development team assures software features functionality on a target across the vertical slice of the Apcon software stack. For example, a support of a new Apcon blade or switch goes through unit level testing which includes blade level software, controller software, and UIs.
At the functional level, a software development team verifies functionality of a software features complex in nature that typically span over multiple hardware targets. At this level a software team also verifies and evaluates stability, high availability, backward compatibility, upgradability and installation of the software.
The output of the unit and functional level testing is recorded and pass/fail rate of the test cases is shared with Software QA team. The exit gate from this development phase is the subject to mutual agreement between software development team and the QA team which must be communicated in Software QA Entrance Agreement document.
Documents that may be delivered in this phase include: SW Development Exit report, detailed unit test plan, functional test plan, defect reports, execution reports with any work around.

## Slide 13: Release from Development phase
This phase starts once the development output is released outside the development group, either internal (SW QA) or external to Apcon (like early demos or beta features).
QA and Customer reported defects and enhancement requests should be recorded in Apcon sw defect tracking repository (such as Mantis).
SW development team addresses reported issues in accordance with sw development process and repeats one of more of verification steps (designer debug, unit test and/or functional test execution) before generating another build and images for further QA validation or customer release.
At the conclusion of the project, the Project Lead chairs the Software Engineering Action Review to capture the improvements for the follow up development projects